## Sheet1
Burndown Chart
User story | Start Hours | Hours spent - day 1 | Hours spent - day 2 | Hours spent - day 3 | Total hours
As a visitor, I want to register myself as a customer, so that I can use the library system. | 44 | 10 | 17 | 17 | 44
As a customer, I want to be able to log in as a customer, so that I can access the library system. | 7 | 2 | 4 | 1 | 7
As a customer, I want to edit my user info, so that it is updated. | 6 | 1 | 2 | 3 | 6
As a visitor, I want to register myself as a customer, so that I can use the library system. | 20 | 5 | 5 | 10 | 20
As a customer, I want to view my name when I log in, so I can identify if I logged to my account. | 2 | 0 | 0 | 2 | 2
As a customer, I want to view items, so that I can borrow them. | 15 | 3 | 6 | 6 | 15
As a customer, I want to borrow item, so that I can use them. | 15 | 1 | 2 | 12 | 15
As a customer, I want borrowed items to be automatically returned, so that other customers who have reserved the item can borrow it. | 6 | 1 | 5 | 0 | 6
As a customer, I want to reserve item, so that I can borrow them later. | 13 | 4 | 4 | 5 | 13
As a customer, I want to be able to see the due date for my borrowed items, so that I can return them in time. | 14 | 3 | 8 | 3 | 14
As a customer, I want to be able to return items which I have borrowed, so that other customers can borrow them. | 15 | 5 | 3 | 7 | 15
As a customer, I want to be alerted when I am entering a queue when I am reserving an already borrowed item, so that I can decide whether to enter the queue or not | 9 | 1 | 2 | 6 | 9
As a customer, I want to search for specific items by their category (book, movie, or videogame) and title, so that I can view and/or borrow them. | 11 | 3 | 3 | 5 | 11
As a customer, I want to be in a queue for reserved items and check my queue position, so that I can borrow them later. | 9 | 3 | 3 | 3 | 9
Actual hours remaining | 186 | 144 | 80 | 0
Estimated hours remaining | 186 | 124 | 62 | 0